## Slide 1: BLOB-FREE
Project Plan
Interdisciplinary project A.Y. 2020/21
Proposed by pROf. dovis, prof. piras and prof. di pietra

## Slide 2: The Problem
Coronavirus is putting at risk many lives; thus some rules must be enforced in order to prevent the spreading of the infection. Two very simple but effective measures are:
Wearing face masks
Avoiding “assemblages” of people

## Slide 3: The solution
Build a computer vision system able to detect “assemblages” of people and able to verify that everyone is wearing a mask, using a cheap digital camera and range camera connected to a Raspberry Pi.
The system can warn users in case a dangerous situation is detected
The management system shows statistics about the issued warnings, so that the managers of the area can take additional preventive measures
The system can be deployed in closed spaces where “assemblages” are frequent (e.g. the corridors of a school or university)

## Slide 4: wBS

## Slide 5: FIRST Steps
Gather data to use in the training of the image recognitions algorithm
Test cameras in different conditions and find the optimal setup
Evaluate the possible image recognition methodologies and choose the most suitable one for this specific task

## Slide 6: Tools
Database for the statistics
RaspberryPi
Digital camera
Range camera
OpenCV library for image recognition
Python

## Slide 7: Workplan
Chart: 
| Project plan definition | User requirements definition | Image recognition methodology evaluation and definition | Training dataset gathering | Cameras testing | Solid image composition algorithm development | Person recognition algorithm | Assamblages detection algorithm | Mask detection algorithm | Statistics visualization | Warning issuing management | Controlled-scenario testing | Results analysis and validation | Real-world scenario testing | Final results analysis
Start Date | 44120 | 44127 | 44141 | 44141 | 44146 | 44169 | 44169 | 44225 | 44225 | 44295 | 44295 | 44323 | 44333 | 44343 | 44350
Duration (days) | 14 | 35 | 21 | 28 | 23 | 56 | 56 | 70 | 70 | 28 | 28 | 10 | 10 | 7 | 22
27/11
SRR
16/10 – 30/10
18/12
PDR
15/1
CDR
7/5
TRR
25/6
FR

## Slide 8: Thank you for the attention!
Team members:
Can Akgol (s274948)
Paolo De Santis (s280398)