## Slide 1: BLOB-FREE
Project Plan
Interdisciplinary project A.Y. 2020/21

## Slide 2: Objectives & Goals
Automate the “surveillance” of an area, in order to prevent CoViD-19 infections
Build a computer vision system able to detect “assemblages” of people and able to verify that everyone is wearing a mask
Issue warnings to the users in the area
Build a management system where the person in charge of the safety of the areas can visualize statistics about “assemblages” and mask wearing, in order to take additional preventive measures
Possibly test the system in a real-world scenario (e.g. Politecnico’s corridors) to verify its effectiveness

## Slide 3: State of the art
The whole World is facing a pandemic; thus it is necessary to take preventive measures to stop infections. Two of the most important ones are:
  Avoiding ”assemblages” of people
  Wear face masks
Computer vision systems can recognize crowds and objects, so it is possible to detect ”assemblages” and masks

## Slide 4: Workplan
Chart: 
| Project plan definition | User requirements definition | Training dataset gathering | Cameras testing | Image recognition methodology evaluation and definition | Data streaming API developement | Image recognition algorithm development | Controlled-scenario testing | Results analysis and validation | Management UI developement | Real-world scenario testing | Final results analysis
Start Date | 44120 | 44127 | 44134 | 44134 | 44141 | 44155 | 44155 | 44260 | 44270 | 44275 | 44304 | 44311
Duration (days) | 14 | 14 | 7 | 7 | 14 | 42 | 101 | 10 | 17 | 29 | 7 | 15

## Slide 5: wBS

## Slide 6: WBS
Blob-free
Image recognition algorithm
Face detection
Mask detection
“Assemblage” detection
Data streaming API
Management UI
Statistics visualization
System set-up
Training dataset gathering
Cameras testing
Methodologies evaluation and definition

## Slide 7: Tools
Server where to store images and the output of the analysis
RaspberryPi
Digital camera
Range camera
OpenCV library for image recognition
Python

## Slide 8: Thank you for the attention!
Team members:
Can Akgol (s274948)
Paolo De Santis (s280398)